## Project Planner
Sydney Air bnb Gantt Chart
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Project Initiation | 1 | 4 |  |  | 100% | bar: PERIODS 1 to PERIODS 5
Form Project Team | 1 | 1 |  |  | 100% | bar: PERIODS 1 to PERIODS 5
Understand Dataset | 1 | 2 |  |  | 100% | bar: PERIODS 1 to PERIODS 2
Define Project Goals and Scope | 3 | 2 |  |  | 100% | bar: PERIODS 3 to PERIODS 4
Project Management | 4 | 2 |  |  | 33% | bar: PERIODS 4 to PERIODS 5; PERIODS 17; PERIODS 28; PERIODS 40; PERIODS 52; PERIODS 58
Regular Team Meetings and Progress Updates | 5 | 1 |  |  | 33% | bar: PERIODS 5 to PERIODS 17; PERIODS 28; PERIODS 40; PERIODS 52; PERIODS 58
Maintain Git Repository and Version Control | 5 | 1 |  |  | 33.33% | bar: PERIODS 5; PERIODS 16; PERIODS 28; PERIODS 40; PERIODS 52; PERIODS 58
Requirements and Analysis | 5 | 5 |  |  | 100% | bar: PERIODS 5 to PERIODS 14
Gather Dataset Details | 5 | 1 |  |  | 100% | bar: PERIODS 13 to PERIODS 18
Identify Analysis and Visualization Needs | 6 | 2 |  |  | 100% | bar: PERIODS 15 to PERIODS 18
Define Functional and Non-functional Requirements | 8 | 2 |  |  | 100% | bar: PERIODS 16 to PERIODS 18
User Interface Design | 10 | 6 |  |  | 100% | bar: PERIODS 10 to PERIODS 19
Create Wireframes for User Interface | 10 | 2 |  |  | 100% | bar: PERIODS 16 to PERIODS 18
Design User Interaction Flow | 12 | 2 |  |  | 100% | bar: PERIODS 16 to PERIODS 18
Define UI Components and Layout | 14 | 2 |  |  | 100% | bar: PERIODS 17 to PERIODS 19
Software Architecture | 16 | 6 |  |  | 100% | bar: PERIODS 17 to PERIODS 20
Select Programming Language and Framework | 16 | 1 |  |  | 100% | bar: PERIODS 17 to PERIODS 19
Design System Components (Frontend, Backend): | 17 | 3 |  |  | 100% | bar: PERIODS 17 to PERIODS 19
Define Data Storage and Retrieval Approach | 20 | 1 |  |  | 100% | bar: PERIODS 20
Part A Submission | 20 | 2 |  |  | 50% | bar: PERIODS 20 to PERIODS 21
Implement Data Analysis Features | 22 | 15 |  |  | 100% | bar: PERIODS 55 to PERIODS 56
Report the information of all listings in a specified suburb | 22 | 3 |  |  | 100% | bar: PERIODS 55
Implement chart showing distribution of property prices | 25 | 2 |  |  | 100% | bar: PERIODS 56
Retrieve all records containing a user-entered keyword (e.g., pool, pet) | 27 | 2 |  |  | 100% | bar: PERIODS 55
Analyse how many customers commented on factors related to cleanliness | 29 | 3 |  |  | 100% | bar: PERIODS 55
Implement search by name feature | 32 | 5 |  |  | 100% | bar: PERIODS 55
Testing and Quality Assurance | 37 | 8 |  |  | 100% | bar: PERIODS 55 to PERIODS 60
Unit Testing for Individual Components | 37 | 3 |  |  | 80% | bar: PERIODS 55 to PERIODS 60
Integration Testing of Modules | 40 | 3 |  |  | 80% | bar: PERIODS 58 to PERIODS 60
User Acceptance Testing | 43 | 2 |  |  | 100% | bar: PERIODS 59 to PERIODS 60
Documentation | 45 | 5 |  |  | 100% | bar: PERIODS 59 to PERIODS 60
User Manual Preparation | 45 | 2 |  |  | 100% | bar: PERIODS 60
Software Design Document Update | 47 | 2 |  |  | 100% | bar: PERIODS 60
Testing Report Compilation | 49 | 1 |  |  | 100% | bar: PERIODS 60
Project Review and Finalization | 50 | 8 |  |  | 100% | bar: PERIODS 55 to PERIODS 60
Review Project Deliverables | 50 | 2 |  |  | 100% | bar: PERIODS 60
Refine User Interface and Functionality | 52 | 2 |  |  | 100% | bar: PERIODS 58 to PERIODS 60
Final Testing and Bug Fixing | 54 | 4 |  |  | 100% | bar: PERIODS 57 to PERIODS 60
Submission Preparation | 58 | 3 |  |  | 100% | bar: PERIODS 60
Compile Required Documents | 58 | 1 |  |  | 100% | bar: PERIODS 60
Review and Ensure Completion | 59 | 1 |  |  | 100% | bar: PERIODS 60
Project Submission | 60 | 1 |  |  | 100% | bar: PERIODS 60