## Project Planner
Project Title
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Project Initiation | 1 | 4 |  |  | 0% | bar: PERIODS 1 to PERIODS 5
Form Project Team | 1 | 1 |  |  | 0% | bar: PERIODS 1 to PERIODS 5
Understand Dataset | 1 | 2 |  |  | 0%
Define Project Goals and Scope | 3 | 2 |  |  | 0%
Requirements and Analysis | 5 | 5 |  |  | 0%
Gather Dataset Details | 6 | 1 |  |  | 0%
Identify Analysis and Visualization Needs | 7 | 2 |  |  | 0%
Define Functional and Non-functional Requirements | 9 | 2 |  |  | 0%
User Interface Design | 11 | 6 |  |  | 0%
Create Wireframes for User Interface | 11 | 2 |  |  | 0%
Design User Interaction Flow | 13 | 2 |  |  | 0%
Define UI Components and Layout | 15 | 2 |  |  | 0%
Software Architecture | 17 | 5 |  |  | 0%
Select Programming Language and Framework | 17 | 1 |  |  | 0%
Design System Components (Frontend, Backend): | 18 | 3 |  |  | 0%
Define Data Storage and Retrieval Approach | 21 | 1 |  |  | 0%
Part A Submission
Implement Data Analysis Features | 22 | 15 |  |  | 0%
Report the information of all listings in a specified suburb | 22 | 3 |  |  | 0%
Implement chart showing distribution of property prices | 25 | 2 |  |  | 0%
Retrieve all records containing a user-entered keyword (e.g., pool, pet) | 27 | 2 |  |  | 0%
Analyse how many customers commented on factors related to cleanliness | 29 | 3 |  |  | 0%
Implement search by name feature | 32 | 5 |  |  | 0%
Testing and Quality Assurance | 37 | 8 |  |  | 0%
Unit Testing for Individual Components | 37 | 3 |  |  | 0%
Integration Testing of Modules | 40 | 3 |  |  | 0%
User Acceptance Testing | 43 | 2 |  |  | 0%
Documentation | 45 | 5 |  |  | 0%
User Manual Preparation | 45 | 2 |  |  | 0%
Software Design Document Update | 47 | 2 |  |  | 0%
Testing Report Compilation | 49 | 1 |  |  | 0%
Project Management | 50 | 2 |  |  | 0%
Regular Team Meetings and Progress Updates | 52 | 1 |  |  | 0%
Maintain Git Repository and Version Control | 53 | 1 |  |  | 0%
Project Review and Finalization | 53 | 5 |  |  | 0%
Review Project Deliverables | 53 | 2 |  |  | 0%
Refine User Interface and Functionality | 55 | 2 |  |  | 0%
Final Testing and Bug Fixing | 57 | 1 |  |  | 0%
Submission Preparation | 58 | 3 |  |  | 0%
Compile Required Documents | 58 | 1 |  |  | 0%
Review and Ensure Completion | 59 | 1 |  |  | 0%
Project Submission | 60 | 1 |  |  | 0%